{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["开发计划"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"开发计划","index":0,"n_rows":27,"n_cols":3,"rows_kept":27,"cut":false,"hidden":false,"merged":[[1,0,5,0],[6,0,11,0],[12,0,15,0],[16,0,21,0],[22,0,24,0],[25,0,26,0],[1,2,5,2],[6,2,11,2],[12,2,15,2],[16,2,21,2],[22,2,24,2],[25,2,26,2]]}
["模块","功能点","开发周期"]
["变更申请","变更申请查询","4月16日~4月19日"]
[null,"变更申请录入"]
[null,"变更申请修改"]
[null,"变更申请删除"]
[null,"变更申请提交"]
["ECO 验证","ECO 验证查询\n","4月20日~4月25日"]
[null,"ECO 验证新增"]
[null,"ECO 验证修改"]
[null,"ECO 验证删除"]
[null,"ECO 验证确认"]
[null,"ECO 验证表结构"]
["ECN 执行","ECN 执行查询","4月26日~4月30日"]
[null,"ECN 执行新增"]
[null,"ECN 进度"]
[null,"展开机型"]
["Demo 申请","Demo 申请查询","5月6日~5月9日"]
[null,"Demo 申请新增"]
[null,"Demo 申请修改"]
[null,"技术要求附件预览"]
[null,"技术要求附件下载"]
[null,"Demo 申请执行"]
["Demo 执行","Demo 执行查询","5月10日~5月15日"]
[null,"Demo 执行新增"]
[null,"Demo 执行进展"]
["统计报表查询","变更管理","5月16日~5月17日"]
[null,"Demo管理"]