{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["开发计划"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"开发计划","index":0,"n_rows":17,"n_cols":3,"rows_kept":17,"cut":false,"hidden":false,"merged":[[2,0,6,0],[7,0,12,0],[13,0,14,0],[15,0,16,0],[2,2,6,2],[7,2,12,2],[13,2,16,2]]}
["模块","功能点","开发周期"]
[null,"环境搭建、模块设计","1月4日~1月9日"]
["订单管理","订单查询"," "]
[null,"订单录入"]
[null,"订单修改"]
[null,"订单删除"]
[null,"订单提交"]
["设备生产管理","设备查询","1月17日~1月26日"]
[null,"设备安装"]
[null,"设备测试"]
[null,"提交验收"]
[null,"设备验收"]
[null,"提交验收单"]
["验收后管理","验收后设备查询","1月27日~2月2日"]
[null,"问题记录"]
["设备追踪查询","查询设备信息列表"]
[null,"查询设备关联问题信息"]